## Tasks
Task ID | Task | Description | Status | Priority | Owner | Created | Due Date | Last Updated
T-001 | Add a left navigation menu | Implement the left navigation menu described in the product brief. | Completed | Medium
T-002 | Show business details on the home page | Show the hotel or shop details, including its logo, on the home page. | Completed
T-003 | Keep the add-product form open | After adding a product, keep the add-product page open until the user closes it, so multiple items can be added without repeatedly selecting Add Product. | Completed
T-004 | Center product images | Adjust product image alignment so each image is centered correctly. | Completed
T-005 | Make barcode optional | Do not require a barcode when adding or editing a product. | Completed
T-006 | Remove edit icons | Remove the edit icon from products and other fields where it is not required. | Completed
T-007 | Reduce POS cart container size | Reduce the size of the cart container on the point-of-sale screen. | Completed
T-008 | Remove icons from current cart fields | Remove unnecessary icons from fields in the current cart. | In Progress
T-009 | Improve POS product refresh speed | Products on the point-of-sale page refresh slowly and updates appear late; improve refresh and update responsiveness. | Completed
T-010 | Prevent layout shifts for long item names | Ensure long item names do not cause the user interface layout to shift or break. | Completed
T-011 | Update checkout page UI | Review and improve the checkout page user interface. | Completed
T-012 | Explore barcode scanner payment and auto-print | Optional feature request: investigate using a barcode scanner in the payment flow and automatically printing the receipt after payment. | Not Started
T-013 | Show detailed bills in sales history | Optional feature request: show a detailed bill in sales history, including total items and customer details when available or required. | Not Started
T-014 | Show inventory totals in navigation area | Show total stock and total item counts in the inventory page navigation/header area. | Completed
T-015 | Review low-stock-only filter | Add a filter to the low-stock-only view, or remove that view if it is unnecessary. | Completed
T-016 | Improve slow-moving product reporting | Slow-moving product data does not appear to update after sales. Add a selectable time period for slow-moving products and/or a field identifying products not sold within the selected period. | Completed
T-017 | Review sales trend report | Verify that the sales trend works correctly and make the report easier to understand. | Not Started
T-018 | Show low-selling products in report | The report currently shows low-stock products where low-selling products are expected; show low-selling products in this section. | Completed
T-019 | Adjust products-page scrollbar padding | Move the scrollbar padding slightly to the right on the products page. | Completed

## Comments
Task ID | Comment / Update | Author | Date | How to use
Add one row per comment/update. Use the matching Task ID from the Tasks sheet.